## Risk Matrix
5 Point Risk Matrix
Project Name: |  | Project Manager |  | Date
Outpatients Critical Conditions |  | JJC |  | 2022-12-13
[8 empty] | Risk | Score
Risk Matrix |  | Severity | [5 empty] | One size fits all | 20
[8 empty] | New Data | 25
|  | Insignificant |  | Minor | Moderate | Major | Severe | Vested Interests | 16
[8 empty] | Lack of Qualificaions | 4
Probability | Almost Certain | Medium |  | High | Very High | Very High | Very High | Corrupt Pharms | 25
[8 empty] | Initial Diagnosis | 8
[8 empty] | Activists | 20
[8 empty] | Patient Data | 8
[8 empty] | Lab Equipment | 3
| Likely | Medium |  | High | High | Very High | Very High
| Possible | Low |  | Medium | High | High | Very High
| Unlikely | Low |  | Low | Medium | Medium | High
| Rare | Low |  | Low | Low | Low | Medium

## Risk Scores
Risk | Probability | Severity | Score | Risk Level
One size fits all | 5 | 4 | 20 | Very High
New Data | 5 | 5 | 25 | Very High
Vested Interests | 4 | 4 | 16 | Very High
Lack of Qualificaions | 1 | 5 | 5 | Medium
Corrupt Pharms | 5 | 5 | 25 | Very High
Initial Diagnosis | 2 | 4 | 8 | Medium
Activists | 4 | 5 | 20 | Very High
Patient Data | 2 | 4 | 8 | Medium
Lab Equipment | 1 | 3 | 3 | Low

## Risk Matrix Key
Level | Likelihood: Chance of risk
1 | Rare: Slim possibility of happening
2 | Unlikely: Could occur but remote
3 | Possible: Might happen
4 | Likely: Expected to occur
5 | Almost Certain: Expected regularly
Severity: Impact on project
1 | Insignificant: Not worth worry about
2 | Minor: Can cause delays or added costs
3 | Moderate: Likely delays or costs
4 | Major: Possible failure
5 | Severe: Definite failure
Risk Level: Setting Priority
1 - 4 | Low: Not much risk
5 - 8 | Medium: Some risk
9 - 14 | High: Major risk
15 - 25 | Very High: Extreme risk