## Risk Register
RISK IDENTIFICATION |  |  | RISK ANALYSIS |  |  |  | PLANNING RISK RESPONSE AND IMPLEMENTATION |  |  | MONITORING AND CONTROL
Date | NAME | Risk Description | Likelyhood (1 to 5) | Impact (1 to 5) | Risk Score (Likelyhood * Impact) | Existing Control | Risk Response | Response Activities | Target Date | ACTIVITY STATUS | COMMENT ON STATUS
2022-04-05 | One Size Fits All | Health regulations insist on one-size-fits-all policy for SARS 2 shots | 5 | 5 | 25 | None | Mitigate | Take account of patient's own health status | 2022-04-30 | Completed | HSE restricting doctors
2022-06-10 | New Data | Regulators fail to consider new clinical data | 3 | 5 | 15 | None | Reduce | Inisist HSE responda to Swedish policy and to consider use of Ivermectin | 2022-05-05 | Completed | Resistance from HSE
2022-09-15 | Vested Interests | Vested interests allowed to suppress safe alternative meds. | 3 | 3 | 9 | None | Mitigate | Raise awareness thro social media | 2022-10-10 | Completed | Resistance from social media main platforms
2022-10-20 | Lack of Qualifications | Physician does not have proper qualificationss | 3 | 4 | 12 | None | Avoid | Implement better scrutiny | 2022-09-05 | Completed | Better cooperation with foreign accredidation
2022-12-05 | Corrupt Pharma | Pharma execs hid adverse reactions to meds. | 4 | 5 | 20 | None | Reduce | Make adverse reaction data widely available | 2023-01-03 | Ongoing | Detraction from HSE
2022-12-07 | Initial Diagnosis | Over-emphasise initial diagnosis from ER and failure to account for disease progression | 2 | 4 | 8 | None | Transfer | Multi-disciplinary team to re-evaluate patients condition | 2023-01-10 | Ongoing | ER doctor reprimanded
2022-12-09 | Activists | Activist groups misrepresented clinical outcomes | 4 | 5 | 20 | None | Transfer | Independent body to investigate | 2023-01-15 | Ongoing | Lobbying by activists
2022-12-11 | Patient data | Patient data corrupted | 2 | 4 | 8 | None | Transfer | Cybersecurity experts reconfigure IT systems | 2023-01-20 | Ongoing | Problem with disparate legacy systems
2022-12-13 | Lab Equipment | Lab equipment could not detect critical markers | 1 | 3 | 3 | None | Transfer | Procure better equipment | 2023-01-23 | Ongoing | Need to stay within budget
RISK REGISTER